AUTOMATION PLATFORM The Complete Build Plan — MERN + AI Agent, Zero-Cost Dev Phase From Idea → MVP → AI-Powered → Launch

| MongoDB | Express | React / Next.js | Node.js | TypeScript | AI Agent |
| --- | --- | --- | --- | --- | --- |

What's in this document Everything in one place: the full MERN architecture, the zero-cost dev-phase stack, all six build phases (including the AI prompt-to-automation agent) each broken into 0%→100% milestones, the complete timeline, and the monetization plan for launch.

# Table of Contents

1. Executive Summary

2. Dev-Phase Stack — $0 vs. Production (Paid, Later)

3. Architecture Overview

4. Phase 0 — Validation & Planning

5. Phase 1 — Core Platform Foundation

6. Phase 2 — Connector SDK & First 10-15 Integrations

7. Phase 3 — AI Prompt-to-Automation Agent

8. Phase 4 — Execution Engine & Reliability

9. Phase 5 — Business Features & Billing (Test Mode)

10. Phase 6 — Hardening, Deployment & Launch

11. Full Timeline Summary

12. Monetization Roadmap (Deferred to Launch)

13. Key Risks to Watch

# 1. Executive Summary

This is the complete, single-reference build plan for your Zapier-style automation platform — built on the MERN stack (MongoDB, Express, React/Next.js, Node.js) with TypeScript, matching your existing skills.

Two things shape this plan end to end:

- Zero-cost dev phase: every tool used while building is chosen for a genuine free tier — nothing costs money until you launch and start billing real users.

- AI-native from the start: users can generate a working automation just by typing what they want, via a dedicated AI Agent phase that plugs into the same Connector SDK every other integration uses.

The plan targets a focused MVP — 10-15 connectors in one niche — rather than trying to match Zapier's 1,000+ integrations on day one. Total estimated timeline: roughly 27-31 weeks (~6.5-7.5 months) with a small team of 1-3 developers, or proportionally longer solo.

# 2. Dev-Phase Stack — $0 vs. Production (Paid, Later)

Rule of thumb for the whole dev phase: if a tool has a genuine free tier with no credit card commitment, use it.

| Layer | Dev Phase — $0 (Free Tier) | Production — Paid (Add Later) |
| --- | --- | --- |
| Frontend Hosting | Vercel free tier (Next.js) — unlimited personal projects | Vercel Pro, or AWS/Cloudflare at scale |
| Backend Hosting | Render free web service, or Railway free tier / Fly.io free allowance | Render/Railway paid tier or AWS ECS |
| Database | MongoDB Atlas Free Cluster (M0 — 512MB, enough for MVP data) | Atlas M10+ dedicated cluster |
| Cache / Queue (Redis) | Upstash Redis free tier (serverless, pay-per-request, free quota) | Upstash paid tier or self-hosted Redis |
| Object Storage | Cloudflare R2 free tier (10GB) or Supabase Storage free tier | S3 / R2 paid usage |
| Auth | JWT (self-rolled) + free OAuth apps (Google/Slack/GitHub dev credentials are free) | Same — auth itself never needs to be paid |
| AI / LLM API | Free credits/tiers: Google Gemini free tier, Groq free tier (fast + generous), or Anthropic/OpenAI trial credits — cap usage per user | Paid LLM API usage, metered into billing |
| Realtime | Socket.io (self-hosted, no cost) on the same free backend host | Same, scaled horizontally |
| CI/CD | GitHub Actions free tier (2,000 min/month) | Same, or paid minutes if needed |
| Monitoring | Sentry free tier (5k errors/month) + free Uptime Robot for uptime checks | Paid Sentry/Better Stack/Grafana Cloud |
| Billing (integration only) | Stripe/Razorpay in TEST MODE — free, no live charges | Same accounts switched to LIVE mode |
| Domain | Use a Vercel/Render subdomain during dev (no cost) | Buy a real domain (~₹700-1000/yr) only near launch |

Respect free-tier limits MongoDB Atlas M0 caps storage at 512MB; Upstash free Redis caps daily commands; LLM free tiers cap tokens/requests per day. Build your own per-user usage caps early so one runaway workflow loop can't burn a whole day's free quota.

# 3. Architecture Overview

- Frontend (Next.js on Vercel free) → REST calls to Backend API

- Backend API (Express on Render/Railway free) → Auth, workflow CRUD, enqueues jobs

- AI Agent Service → receives a natural-language prompt, calls the LLM with your Connector SDK as context, returns a structured draft workflow

- BullMQ Queue (Upstash Redis free) → holds pending workflow executions

- Worker process(es) → executes the DAG node-by-node via the Connector SDK, handles retries

- Connector SDK → uniform interface every third-party app (and the AI-agent node type) implements

- MongoDB Atlas (free M0) → users, workflows (DAG as embedded JSON), connectors, OAuth tokens (encrypted), execution logs, AI-generation history

- Socket.io → live execution status + live AI-generation streaming back to the UI

- Object storage (R2/Supabase free) → large payloads/attachments referenced by execution logs

# 4. Phase 0 — Validation & Planning

Duration: 1-2 weeks Cost: $0 Goal: Confirm there's a real, narrow niche worth building for before writing production code.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Kickoff | Pick the target niche (e.g. AI + BPO/SMB automation). List 10-15 apps that niche actually uses daily. |
| 20% | User interviews | Talk to 10-15 potential users; document their top 5 manual/repetitive tasks. |
| 40% | Trigger/Action map | For each of the 10-15 apps, list exact triggers and actions you'll support (e.g. "New WhatsApp message", "Create row in Sheet"). |
| 60% | Pricing model decided | Choose task-based metering vs flat subscription — this decision shapes your DB schema for usage tracking later (not activated until launch). |
| 80% | Wireframes | Rough Figma/paper wireframes of workflow builder, connector list, dashboard. |
| 100% | Go/No-Go | Written 1-page MVP spec: niche, 10-15 connectors, pricing model, target launch date. Signed off before Phase 1 starts. |

# 5. Phase 1 — Core Platform Foundation

Duration: 4 weeks Cost: $0 Goal: Auth + empty workflow builder + ONE real end-to-end automation working.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Repo setup | Monorepo (Turborepo/Nx) with apps/frontend (Next.js), apps/backend (Express), apps/worker (Node). Shared TypeScript types package. |
| 15% | Auth service | Signup/login, JWT issuing + refresh, org/team model in MongoDB (users, organizations collections). |
| 30% | Workflow data model | MongoDB schema: workflows collection storing nodes[] and edges[] as embedded documents (DAG as JSON). |
| 45% | Workflow builder UI (v1) | React Flow canvas: drag nodes, connect edges, save/load workflow to backend via REST. |
| 60% | Redis + BullMQ wired | Upstash-backed queue connected to backend; "Run Workflow" button enqueues a job. |
| 75% | First worker process | Worker picks up job from queue, logs execution start/end to MongoDB. |
| 90% | First real connector (Gmail → Slack) | Full OAuth for Gmail + Slack, trigger on new email, post message to Slack — running through the real queue/worker pipeline. |
| 100% | Phase exit demo | You can log in, build a 2-node Gmail→Slack workflow in the UI, save it, trigger it for real, and see the result — start to finish, no shortcuts. |

# 6. Phase 2 — Connector SDK & First 10-15 Integrations

Duration: 6 weeks Cost: $0 Goal: A reusable connector interface + your niche's full connector set + field mapping.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Connector interface spec | Finalize TypeScript interface: authenticate(), listTriggers(), listActions(), trigger(config), execute(action, input), refreshToken(). |
| 15% | OAuth2 abstraction layer | One reusable OAuth flow (Passport.js strategies) supporting Google, Slack, Microsoft, GitHub, generic OAuth2 apps. Tokens AES-256 encrypted in MongoDB. |
| 30% | API-key/webhook auth support | Extend the SDK to also support API-key and webhook-signature auth (for apps like Stripe, Razorpay, Notion API-key mode). |
| 45% | 3 connector archetypes built | One polling-trigger connector (e.g. Google Sheets new row), one webhook-trigger connector (e.g. Stripe payment), one action-only connector (e.g. send Slack message). |
| 60% | Remaining connectors (up to 10-15) | Build out the rest of your niche's app list, reusing the SDK — no special-casing per app. |
| 75% | Field-mapping UI | UI for mapping Node A's output fields into Node B's input fields — this is the feature that makes it feel like real Zapier, budget real time here. |
| 90% | Connector marketplace UI | Simple searchable list/grid of available connectors in the builder sidebar. |
| 100% | Phase exit demo | A user can connect 3+ real accounts via OAuth and chain a 3-4 step workflow across different connector types, with correct field mapping. |

# 7. Phase 3 — AI Prompt-to-Automation Agent

Duration: 4-5 weeks (can run parallel with Phase 4) Cost: $0 (free LLM tier + per-user caps) Goal: A user types what they want in plain language, and the system generates a working draft automation — reviewed and activated by the user, never auto-run.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Connector manifest generator | Auto-generate a machine-readable JSON summary of every connector's triggers/actions/config fields from your existing Connector SDK — this becomes the AI's "toolset." |
| 15% | Prompt-to-JSON pipeline | Send user prompt + manifest to the LLM using structured/tool-calling output mode, forcing a response that matches your exact workflows schema (nodes[]/edges[]). |
| 30% | Validation layer | Backend checks the generated DAG: every connector/action referenced actually exists, required config fields are present, no cycles, no orphaned nodes. |
| 45% | Draft rendering into builder | Generated workflow opens directly in the React Flow canvas as an editable, unactivated draft — never runs automatically. |
| 60% | Connect-missing-accounts flow | If the AI references a connector the user hasn't authenticated yet, prompt them to connect it before the workflow can be activated. |
| 75% | Clarification loop | If the prompt is ambiguous (e.g. "notify me" without a channel), the agent asks one follow-up question instead of guessing — via a simple chat-style input above the canvas. |
| 90% | AI-agent node type | A new connector type (implementing the same SDK interface) that runs mid-workflow — summarizing, classifying, or extracting data using the LLM as a workflow step, not just at generation time. |
| 100% | Phase exit demo | Type: "When I get a new lead in WhatsApp, summarize it and add it to my Google Sheet, then notify me on Slack" → a correct, editable 4-node draft appears, missing connections are flagged, and activating it runs correctly end-to-end. |

Keeping the AI agent free during dev Use Groq (free tier, very fast inference) or Google Gemini's free tier for the agent during development. Cap generations per user per day (e.g. 10/day) so a runaway loop can't burn your whole free quota. Only move to a paid model once billing is live and funded by real subscriptions.

# 8. Phase 4 — Execution Engine & Reliability

Duration: 5 weeks Cost: $0 Goal: Workflows that survive real-world API failures without losing data.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | DAG execution engine spec | Define topological execution order; output of Node A becomes input of Node B via the field-mapping config. |
| 20% | Sequential DAG executor | Worker executes nodes in dependency order, persisting output of each node to the execution log. |
| 40% | Retry logic | Exponential backoff per node (1s → 5s → 20s → 1min) via BullMQ's built-in retry + custom backoff strategy. |
| 55% | Error handling & partial-failure state | Mark exactly which node failed; allow "replay from this step" instead of re-running the whole workflow. |
| 70% | Rate limiting per connector | Token-bucket rate limiter in Redis per connector/per-user to respect each third-party API's limits. |
| 85% | Execution logs UI + Socket.io live status | Users see live run status (running/success/failed) per node, with full input/output/error per step. |
| 100% | Phase exit demo | Deliberately break a downstream API mid-run (mock a 500 error) — workflow retries correctly, then either recovers or fails gracefully with a clear, replayable error state. |

# 9. Phase 5 — Business Features & Billing (Test Mode)

Duration: 4 weeks Cost: $0 (Stripe/Razorpay TEST mode) Goal: You can charge users and they can self-serve manage their account — wired now, switched live only at launch.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Usage metering design | Decide the billing unit (task executions, AI generations, active workflows) based on Phase 0 pricing decision. Add usage counters to MongoDB. |
| 20% | Stripe/Razorpay integration (test mode) | Free tier + 1-2 paid tiers wired to test-mode payment processing and webhook-based plan updates — no live charges yet. |
| 40% | Usage dashboard (user-facing) | Users see their own run history, AI-generation count, success rate, and current usage against plan limits. |
| 60% | Team & role-based access | Invite teammates to an org, shared workflows, admin vs member permission levels. |
| 80% | Notifications | Email + Slack alert when a workflow fails, using a free-tier transactional email provider (e.g. Resend free tier). |
| 100% | Phase exit demo | A test payment goes through Stripe/Razorpay test mode, plan limits are enforced, and a teammate can be invited and use a shared workflow with correct permissions. |

# 10. Phase 6 — Hardening, Deployment & Launch

Duration: 3-4 weeks Cost: Paid begins here Goal: Ship safely to real users and be able to operate it. This is the only phase where real money gets spent.

| % | Milestone | What Gets Built / Done |
| --- | --- | --- |
| 0% | Security audit checklist | Review: multi-tenant data isolation (org-scoped MongoDB queries everywhere — critical now that an AI agent writes workflows too), secrets encryption, dependency vulnerabilities. |
| 20% | Load testing | Load-test the queue/worker layer at your expected concurrency (e.g. k6 or Artillery against BullMQ). |
| 40% | Dockerize everything | Dockerfiles for frontend, backend, worker; docker-compose for local + staging. Skip Kubernetes for MVP — it's overkill this early. |
| 60% | Monitoring & alerting live | Sentry + Uptime Robot (or upgrade to paid Grafana Cloud) tracking error rate, queue depth, API latency. |
| 80% | Private beta | Onboard the 10-15 users interviewed in Phase 0; collect structured feedback on bugs, missing connectors, and AI-generation accuracy. |
| 100% | Public launch | Public sign-up open, billing switched to LIVE mode, paid infra upgraded where needed, on-call process defined for the first weeks post-launch. |

# 11. Full Timeline Summary

| Phase | Duration | Exit Criteria |
| --- | --- | --- |
| Phase 0 — Validation | 1-2 weeks | Signed-off MVP spec — $0 |
| Phase 1 — Core Platform | 4 weeks | One real automation runs end-to-end — $0 |
| Phase 2 — Connector SDK | 6 weeks | 10-15 connectors live with field mapping — $0 |
| Phase 3 — AI Agent | 4-5 weeks (parallel w/ Phase 4) | Prompt generates a correct, editable draft workflow — $0 |
| Phase 4 — Execution Engine | 5 weeks | Retries/failure recovery proven under a forced failure — $0 |
| Phase 5 — Billing (test mode) | 4 weeks | Test payment processed, teams working — $0 |
| Phase 6 — Launch | 3-4 weeks | Public launch, LIVE billing, paid infra switched on |

Total: roughly 27-31 weeks (~6.5-7.5 months) for a small team of 1-3 developers, with Phase 3 (AI Agent) overlapping Phase 4 to save calendar time. Solo, expect proportionally longer — the phase order and 0%→100% checkpoints still apply.

# 12. Monetization Roadmap (Deferred to Launch)

Nothing before Phase 6 requires spending money. Billing is built and tested in Phase 5 but stays in test mode until launch. This section is the plan for when money starts moving — don't act on it early.

- Free tier: capped workflow runs/month, capped AI generations/month, community support only.

- Paid tier(s): higher run limits, more AI generations, priority execution, team seats.

- AI usage becomes a real cost input once on a paid LLM — meter it per-generation the same way you meter task executions, and price accordingly.

- Only after Phase 6 launch: upgrade MongoDB Atlas, Upstash, hosting, and the LLM API from free tier to paid, funded by actual subscription revenue — not before.

# 13. Key Risks to Watch

- Free-tier throttling mid-demo — always build per-user usage caps into your own app, don't rely on the provider's error message as your only limit.

- AI-generated workflows must never auto-activate — validation + human review is a safety requirement, not just UX polish.

- Connector maintenance debt — third-party APIs change over time; budget ongoing time per connector, not just initial build time.

- Field-mapping UI is consistently underestimated — this is what separates a real automation tool from a toy demo.

- Don't reach for Kafka/Kubernetes/Temporal on day one — BullMQ + Docker Compose comfortably handles MVP-scale load.

- Multi-tenant data isolation — every MongoDB query must be scoped to the organization, doubly important once an AI agent is writing workflows on a user's behalf.

- OAuth token refresh edge cases (revoked access, expired refresh tokens) will be your most common support ticket — build clear reconnect UX early.

Next step: I can scaffold the Phase 1 monorepo structure, the Connector SDK TypeScript interface, or the AI Agent Service (prompt → structured workflow JSON) in code — whichever you want to start with.